## Admin
Module | Menu | SubMenu | Function | Sub- Function | Description
2019-12-09
Admin | Setting | Module | View module details |  | After clicking view module details it doesn't show anything.

## Reservation
Module | Menu | SubMenu | Function | Sub- Function | Description | Status
2019-08-09
Reservation |  | All reservation |  | Invoice | In invoice while showing costing for services has been taken,
description should be shown like for restaurent fried rice,laudry
washing clothes and so on.But service description is not showing.
|  | New reservation |  |  | Discount and Promo code is not working.
|  | Invoice |  |  | After paying full amount the adjusted amount is showing in due.
Inventory items can be added after check out.Need to be resolved.
2019-09-09
| Front office | Room | Room List |  | In room list,room type should be same as after updated the room type. | Fixed
In room view it is showing same as updated one.But In room list room
type is not showing correctly.

## Room
2019-09-09
Module | Menu | SubMenu | Function | Sub- Function | Description | Status
Front office | Room | Room List |  |  | In room list,room type should be same as after updated the room type. | Fixed
In room view it is showing same as updated one.But In room list room
type is not showing correctly.

## service
Module | Menu | SubMenu | Function | Sub- Function | Description | Status
2019-09-09
Front office | Services | Item billing | All inventory order | Edit | Edit button is not working properly.
|  |  |  | Delete | Delete button is not working properly.

## Report
Module | Menu | SubMenu | Function | Sub- Function | Description | Status
Front office | Report | Guest report |  |  | In the report instead of reservation id,it should be reservation number.
|  | Room status report |  |  | It should be shown how many times the room status has been updated.
It is showing updated status only for 5times not more than that.

## Laundry
Module | Menu | SubMenu | Function | Sub- Function | Description
2019-12-09
Restaurant | Dashboard |  |  |  | Order summery should be shown in all restaurant today's
summery.No Order Yet is showing after odering food.
Laundry | Laundry Order |  | Add New Laundry Service |  | It will show unit price then will count total price.Unit price is
not showing that's why total price is zero in payment.